## Slide 1
ELG5901-EG00
Project Proposal Presentation
Network optimization and analysis using AI
Group: AI_AWS3_MAY2022

## Slide 2: Contributors:
Abdelrhman Gaber Youssef Saad Rezkallah
Abdulrahman Muhammad AbdulSalam Ahmed
Basma Reda Shaban Abd-Elsalam Abd-Elwahab
Amir Safwat Halim Youssef
Ali Amin El-Sayed Mahmoud El-Sherif
ID: 300327290
ID: 300327218
ID: 300327209
ID: 300327305
ID: 300327246
Project Proposal-Ali El-Sherif – 300327246

## Slide 3: Mentorship and sponsors:
Project Mentor: Dr. Anas Youssef
Project Sponsor: Amazon Web Services (AWS)
Project Supervisor: Dr. Murat Simsek
Project Proposal-Ali El-Sherif – 300327246

## Slide 4: Table of contents
Project Problem Definition
Potential Benefits to Sponsor/Users: Identify the end user(s)
Solution Design and Implementation
Project Proposal-Ali El-Sherif – 300327246

## Slide 5: Project Problem Definition
5G network is a bit more complex than the previous generations and in need of regular enhancements as it communicates with a much higher number of devices. Nevertheless, spectrum efficiency decaying and beamforming selection are considered as major aspects in this case.
The main features to work on when applying artificial intelligence are:
  Network optimization for better network establishments.
  Failure detection forecasting to provide lower maintenance cost and minimalize maintenance work.
Project Proposal-Ali El-Sherif – 300327246

## Slide 6: Project Problem Definition
Different technologies have been used in other models like multiple-input multiple-output (MIMO) and millimeter wave (mm-wave) communications. In MIMO, each base station can transmit data streams of high-speed data to each device simultaneously. Nevertheless, in mm-wave, the base station can make use of high frequency spectrum to overcome the shortage of bandwidth and provide user’s equipments with the availability of more bandwidth.
To settle cell site dilemmas, five aspects will need improvement which are:
  Mobility
  Spectrum
  User’s peak data rate
  User’s experience data rate
  Network energy efficiency
Project Proposal-Ali El-Sherif – 300327246

## Slide 7: Potential Benefits to Sponsor/Users
AWS Private 5G is currently available in the following AWS Regions: US East (Ohio), US East (N. Virginia), and US West (Oregon).
AWS has a service category in augmented reality (AR) and virtual reality (VR) fields that require 5G technology.
Optimization of beam selection efficiency using deep learning which will lead to the increase of spectrum efficiency which is mostly beneficial to the company/users.
Any user using these enhancements through a service will experience convenience through AWS or any other network applied to it.
Project Proposal-Ali El-Sherif – 300327246

## Slide 8: Solution Design and Implementation
Methodology
Data/Testing Plan
Project Context
Project Plan
Project Proposal-Ali El-Sherif – 300327246

## Slide 9: Methodology
Using deep learning approaches, one of the problems is spectrum efficiency and the other is beamforming selection that will be solved based on deep neural networks.
Amazon EC2 will be used to train the model while Amazon Sagemaker will be used to evaluate it.
Classical machine learning techniques will be used to predict network failure either bagging, boosting or stacking techniques and compare between them to come up with the best model.
Anomalies detection and deal with them to build a time series model that can forecast whether the network will fail or not based on the readings. Amazon deepAR , ARIMA and SARIMA will be used and the best model will be chosen based on their performances.
Project Proposal-Ali El-Sherif – 300327246

## Slide 10: Data/Testing Plan
The dataset will be split into 3 fragments (training, validation and testing).
Whether Amazon Sagemaker or jupyter notebook will be used for testing.
Two types of data are provided in the dataset, images that will be used in beamforming selection and tabular data that will be used in forecasting, failure detection, optimization of network and beamforming selection.
Each part of the data should be/transformed into the right format to be used later on.
Data should be checked whether it is clean or not, has outliers or anomalies.
All the detected issues should be fixed to make the dataset ready for the training process.
The dataset is provided by Para-State university as a challenge that the university has posted based on a simulation made by its staff, any team around the globe can compete in this challenge. The following are the main steps in data/testing plan:
Project Proposal-Ali El-Sherif – 300327246

## Slide 11: Project Context
Amazon sagemaker
Amazon EC2 instances
Amazon EC2 auto-scaling
Amazon S3
Amazon Lambda
AWS IAM
Amazon Cloudwatch
Amazon Kinesis
Environments and services to be used:
Amazon web services that will possibly be used:
Also, jupyter notebook will be used.
Project Proposal-Ali El-Sherif – 300327246

## Slide 12: Project Context
 | Project Sponsor (AWS) | Egypt Mentor (Dr. Anas Youssef) | uOttawa Supporter (Dr. Murat Simsek)
Summary of expertise and guidance | Knowledge and technical guidance and assistance with previous expertise in the field | Knowledge and technical guidance and paperwork recommendations | Knowledge and technical guidance and paperwork recommendations
Job title |  | Research Assistant & Application Developer at University of Calgary | Engineer in residence and Research Associate
Type of interaction | Physical meeting or online meeting | Online meeting | Online meeting
Frequency of interaction | Every two weeks or when technical or knowledge assistance needed | Weekly or when technical or knowledge assistance needed | Every two weeks
Individuals/organizations and key dependencies:
Project Proposal-Ali El-Sherif – 300327246

## Slide 13: Project Context
Benefits to end users:
Higher dependency
Higher data rate
Higher availability
Better connection in mobility
Project Proposal-Ali El-Sherif – 300327246

## Slide 14: Project Plan
Iteration | Milestone Deliverables | Hours | Iteration | Milestone Deliverables | Hours
Project Proposal Presentation – August 28th Project Proposal Final Draft – September 14th |  |  | Minimum Viable Prototype Présentation – Octobre 30th |  | 
1 | Finalizing project’s proposal Description of problem domain Literature review completion Development Environment (Amazon Web Services) setup Datasets and Test Environment setup Completion of defining the Methodology, Algorithms, Models Detailed Project Plan Project Proposal Presentation | 24 | 2 | Establish the project architecture based on the MVP pattern Collect the data Data understanding Cleaning and form exploratory data analysis on the dataset Building classical machine learning models to predict the failure in the network Compare between the classical models and select the best among them Examine test results Sponsor and mentor reviewing and feedback Make a presentation regarding the project architecture based on the MVP pattern and the previously done work in this section | 72
Project Proposal-Ali El-Sherif – 300327246

## Slide 15: Project Plan
Iteration | Milestone Deliverables | Hours | Iteration | Milestone Deliverables | Hours
Beta Release Presentation – December 18th |  |  | Final Report, Internship Evaluation, (Team Peer Review) – January 15th |  | 
3 | Build a time series model that can forecast whether the network will fail or not based on the readings using amazon deepAR, ARIMA and SARIMA Compare between different time series techniques to select the best model Examine test results Sponsor and mentor reviewing and feedback Make beta presentation | 84 | 4 | Building deep learning model to help with beamforming selection Examine test results Sponsor and mentor reviewing and feedback Final deployment of Technology Final report finalizing and Handing off the Documentation Evaluation Forms | 60
 |  |  | Total Hours |  | 240
Project Proposal-Ali El-Sherif – 300327246

## Slide 16: Detailed Project Plan
Iteration | Tasks | Hours | Iteration | Tasks | Hours
1 | Discuss project with mentor Research approaches, relevant technologies Plan project schedule and deliverables Literature review | 6 | 3 | Demonstrate progress in terms of minimum viable prototype to project mentor Complete requirements analysis and finalize evaluation criteria with project mentor Create presentation (Screen shots of current status, Requirements, Criteria) | 8
Project Proposal Presentation – August 28th Project Proposal Final Version for Marks – September 14th |  |  | Minimum Viable Prototype Presentation – October 30th |  | 
2 | Problem understanding Finalizing project’s proposal Description of problem domain Literature review completion Development Environment (Amazon Web Services) setup Datasets and Test Environment setup Completion of defining the Methodology, Algorithms, Models Detailed Project Plan Project Proposal Presentation | 10 | 4 | Establish the project architecture based on the MVP pattern Collect the data Data understanding Data cleaning and preprocessing Form exploratory data analysis on the dataset | 17
Project Proposal-Ali El-Sherif – 300327246

## Slide 17: Detailed Project Plan
Iteration | Tasks | Hours | Iteration | Tasks | Hours
5 | Building classical machine learning models to predict the failure in the network Compare between the classical models and select the best among them Examine test results Make a presentation regarding the project architecture based on the MVP pattern and the previously done work in this section Validate project results with project mentor. | 30 | Beta Release Presentation – December 18th |  | 
6 | Demonstrate project in terms of completion but not finalized release to project mentor Finalize design. Finalize TODO list. Finalizing the presentation based on the feedbacks and the possible edits before submission (Screen shots of current status, Results, Design) | 25 | 8 | Final demonstration and delivery of results to project mentor Build a time series model that can forecast whether the network will fail or not based on the readings using amazon deepAR, ARIMA and SARIMA Compare between different time series techniques to select the best model Examine test results Sponsor and mentor reviewing and feedback Complete Project Mentor Evaluation Form, and Team Peer Review. Draft report to project mentor and projects coordinator. Submit final report. Make beta presentation | 84
Project Proposal-Ali El-Sherif – 300327246

## Slide 18: Detailed Project Plan
Iteration | Tasks | Hours
Final Report, Internship Evaluation, (Team Peer Review) – January 15th | Building classical machine learning models to predict the failure in the network Compare between the classical models and select the best among them Examine test results Make a presentation regarding the project architecture based on the MVP pattern and the previously done work in this section Validate project results with project mentor. | 30
9 | Building deep learning model to help with beamforming selection Examine test results Sponsor and mentor reviewing and feedback Final deployment of Technology Final report finalizing and Handing off the Documentation Evaluation Forms | 60
Total Hours |  | 240
Project Proposal-Ali El-Sherif – 300327246

## Slide 19
Thank You